## Gantt Chart
GANTT CHART
PROJECT TITLE |  | Safari Snapshot |  |  |  |  | ORGANIZATION NAME |  | SUNY New Paltz
PROJECT ADVISOR |  | Anthony Denizard |  |  |  |  | DATE |  | 2022-01-24
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | W1 1/31/2022 | W2 2/07/2022 |  | W3 2/14/2022 | W4 2/21/2022 | W5 2/28/2022 | W6 3/07/2022 | W7 3/14/2022 | W8 3/21/2022 | W9 3/28/2022 | W10 4/04/2022 | W11 4/11/2022 | W12 4/18/2022 | W13 4/25/2022 | W14 5/02/2022
1 | Project Conception and Initiation
1.1 | Setting up Github | Everybody | 2022-01-31 | 2022-02-04 | 4
1.1.1 | Setting up Webex Account | Everybody | 2022-01-31 | 2022-02-04 | 4
1.1.2 | Setting up XAMPP / Unreal Engine | Everybody | 2022-01-31 | 2022-02-04 | 4
1.1.3 | Assigning Group Leader | Everybody | 2022-01-31 | 2022-02-04 | 4
1.1.4 | Creating Group Unreal Environment | Everybody |  |  | 0
1.1.5 | Assigning Individual Roles | Everybody |  |  | 0
1.1.6 | Creation of UML Diagrams | Everybody |  |  | 0
1.1.7 | Creation of Use Case Diagrams | Everybody
1.1.8 | Work on Landscape | AV/CP
1.1.9 | Work on Animal AI | JO/AI
1.2.0 | Create List of Quests | Everybody
2 | Design / Components
| Bait Launchers | DC | 2022-03-21
| Design Animal Detection Mechanism | BP | 2022-02-21
| Designing Photo-Taking Mechanism | BP | 2022-02-14 | 2022-02-25
| Design Photo Storage Structure | BP | 2022-03-07
| Implement Location Based Quests | LS | 2022-04-06 | 2022-04-13 | 7
| Implement Interaction Quests | LS | 2022-04-06 | 2022-04-13 | 7
| Implement Picture Taking Quests | LS | 2022-04-13
2.1 | Visuals
2.1.1 | Finding Textures | Everybody
2.1.2 | Creating Animal Animations | JO/AI |  |  | 0
2.1.3 | Finding Animal Models | JO/AI
2.1.4 | Connecting Animations to Models | JO/AI |  |  | 0
2.1.5 | Designing Environments | AV/CP
2.1.6 | Finding Guide NPC model | LS |  |  | 1
2.1.7 | Connecting Animations to Guide Model | LS |  |  | 3
2.1.8 | Create New Quest Display for Guide Model | LS | 2022-03-02
| Add Player Body and animations | BP
2.2 | GUI/Menus
2.2.1 | Create Title Screen | DC | 2022-01-31 | 2022-02-06 | 0
2.2.2 | Camera GUI | BP
2.2.4 | Design of Animal Encyclopedia (Pokedex) ~ | AI
2.2.5 | Design of Question form ~ | AI
2.2.6 | Design of photo album ~ | AI |  |  | 0
2.2.7 | UI | DC | 2022-01-31 | 2022-03-15 | 45
2.2.8 | Display Quest Dialogue | LS | 2022-02-28 | 2022-03-06 | 9
2.2.9 | Design Quest Log | LS | 2022-03-06 | 2022-03-15 | 9
2.2.10 | HUD Active Quest Display | LS | 2022-03-15 | 2022-04-06 | 22
2.3 | Audio
2.3.1 | Finding/Creating Animal Sounds | JO |  |  | 0
2.3.2 | Finding/Creating Music | BP |  |  | 0
2.3.3 | Finding/Creating Player Sounds | JO
2.3.4 | Finding/Creating Environment Sounds | TBD |  |  | 0
2.4 | Data Management
2.4.4 | Collecting Animal Data | BP
2.4.6 | User Photo Management | TBD
3 | Assembly of Components
3.1 | Inserting Animals into Biomes | JO |  |  | 0
3.3 | Connecting SFX to Animals | JO/AI
3.5 | Connecting Camera to Animal Models | BP | 2022-03-05 |  | -43985
3.7 | Connecting Quest System to Pictures of Animals | LS | 2022-04-20 |  | 0
3.8 | Adding bait to Quest Rewards | LS | 2022-04-20 |  | 0